# Action Items

Abbreviations for partners are explained in the section partner list.

- OU and UKARL to provide technical infrastructure for proposal writing [until 28.01]

- ALL to provide your contact details such as email, telephone and fax to Peter (haase@aifb.uni-karlsruhe.de) [until 28.01.]

- WP LEADERS (R&D and case studies) to provide half-page description of their WP to Peter (haase@aifb.uni-karlsruhe.de) [until 28.01.]

- ALL to provide financial details to Enrico (e.motta@open.ac.uk) [until 04.02.]

  - cost model according to EU guidelines (AC, FC, ..)

  - personal cost per person per year

- ALL to suggest members for the advisory board to York (sure@aifb.uni-karlsruhe.de) [until 04.02.]

The following action items (AI) should be managed via the technical infrastructure to be provided as AI-1:

- CORE MEMBERS to provide B.1, B.2 and B.3 [until 22.02.]

- WP LEADERS to provide WP descriptions for B.4.1 [until 22.02.]

- CORE MEMBERS to clarify and provide B.4.2 and B.4.3 [until 22.02.]

- OU to provide descriptions for B.4.4 [until 22.02.]

- ALL to provide paragraph describing their institution for B.5 [until 04.02.]

- CORE MEMBERS to clarify B.5.1, B.5.2 and B.5.3 [until 22.02.]

- CORE MEMBERS to provide descriptions for B.6 [until 22.02.]

- CORE MEMBERS to provide descriptions for B.7 [until 22.02.]

- CORE MEMBERS to provide introduction (a, b, c, partially d) for B.8 [until 01.03.]

- WP LEADERS to provide WP descriptions (d) for B.8 [until 22.02.]

- CORE MEMBERS to provide B.9 [until 22.02.]

- UPM to provide B.10 [until 22.02.]

More action items will follow, e.g. the provision of further EU forms. A following update of this document will include e.g. the completed partner contact details.

# Agreed Timeline

- 21.01.: 1st F2F meeting (consortium)

- 28.01.: Update of short proposal

- xx.02.: Meeting with EU (OU, UKARL, UPM)

- 22.02.: WP descriptions ready

- 01.03.: Integrated Proposal

- xx.03.: 2nd F2F meeting (core partners)

- 15.03.: Final proposal

- 18.03.: Submission online

- 22.03.: Closing 4th Call

# Agreed Budget Planning

- Duration: 4 years (positive feedback from EU)

- Funding: ~12 MEUR

# Agreed WP Structure

Underlined are WP leaders, ‘*’ indicates major contribution of a partner in this WP

Abbreviations see section on partner list

## Life Cycle of Networked Ontologies

UPM*, CNR*, USHEFF*, UKARL*

## Collaboration for Networked Ontologies

OU*, ONTO*, UPM*, CNR*, INRIA*, JSI, USHEFF*, ISOCO*

## Dynamics for Networked Ontologies

UKARL*, UPM, INRIA*, JSI*, UKOB*, OU

## Human-Ontology Interaction

ADUNA*, ISOCO, OU*, UKARL, JSI

## Context Sensitivity

JSI*, USHEFF, UKARL, ISOCO, CNR, UKOB*

## Distributed Infrastructure

ONTO*, SAG*, UPM, OU, UKARL, ISOCO*, ADUNA*

## Nature Case Study

NATURE, OU

## UN FAO Case Study

FAO, CNR

## Software AG Case Study

SAG

## Pharma Innova Case Study

PHARMA, ISOCO

## Exploitation

SAG, iSOCO, Onto, Aduna

## Dissemination

JSI, OU, UPM

## Technical Management

UKARL, OU, UPM

## Consortium Management

OU

# Partner List

Core members are partners 1 to 4.

- OU - The Open University, UK

- UKARL - Universität Karlsruhe (TH), Germany

- UPM - Universidad Politécnica de Madrid, Spain

- ISOCO - Intelligent Software Components S.A., Spain

- INRIA - Institut National de Recherche en Informatique et en Automatique Grenoble, France

- USHEFF - The University of Sheffield, UK

- UKOB - Universität Koblenz-Landau, Germany

- JSI - Josef  Stefan Institute, Slowenia

- CNR – CNR, Laboratory for Applied Ontology, Italy

- ONTO - ontoprise GmbH, Germany

- ADUNA - Aduna B.V., The Netherlands

- SAG - Software AG, Germany

- NATURE - Nature Publishing Group, UK

- FAO - United Nations, Food and Agriculture Organization, Italy

- PHARMA - Pharma Innova, Spain

# Contact Details

## OU - The Open University, UK

Enrico Motta

Email:

Tel:

Fax:

Martin Dzbor

Email:

Tel:

Fax:

## UKARL - Universität Karlsruhe (TH), Germany

Rudi Studer

Email: studer@aifb.uni-karlsruhe.de

Tel: +49 721 608 3923

Fax: +49 721 608 6580

York Sure

Email: sure@aifb.uni-karlsruhe.de

Tel: +49 721 608 6592

Peter Haase

Email: haase@aifb.uni-karlsruhe.de

Tel: +49 721 608 3705

Marc Ehrig

Email: ehrig@aifb.uni-karlsruhe.de

Tel: +49 721 608 7362

## UPM - Universidad Politécnica de Madrid, Spain

Asun Gomez-Perez

Email:

Tel:

Fax:

## ISOCO - Intelligent Software Components S.A., Spain

Richard Benjamins

Email:

Tel:

Fax:

## INRIA - Institut National de Recherche en Informatique et en Automatique Grenoble, France

Jerome Euzenat

Email:

Tel:

Fax:

## USHEFF - The University of Sheffield, UK

Hamish Cunningham

Email:

Tel:

Fax:

Kalina Bontcheva

Email:

Tel:

Fax:

## UKOB - Universität Koblenz-Landau, Germany

Steffen Staab

Email:

Tel:

Fax:

Bernhard Tausch

Email:

Tel:

Fax:

## JSI - Josef  Stefan Institute, Slowenia

Marko Grobelnik

Email:

Tel:

Fax:

Dunja Mladenic

Email:

Tel:

Fax:

## LAO - Laboratory for Applied Ontology, Italy

Nicola Guarino

Email:

Tel:

Fax:

Aldo Gangemi

Email:

Tel:

Fax:

## ONTO - ontoprise GmbH, Germany

Juergen Angele

Email:

Tel:

Fax:

Moritz Weiten

Email:

Tel:

Fax:

## ADUNA - Aduna B.V., The Netherlands

Jeroen Wester

Email:

Tel:

Fax:

## SAG - Software AG, Germany

Walter Waterfeld

Email:

Tel:

Fax:

Harald Schoening

Email:

Tel:

Fax:

## NATURE - Nature Publishing Group, UK

Timo Hannay

Email: t.hannay@nature.com

Tel: +44 20 7843 4750

Fax:

## FAO - United Nations, Food and Agriculture Organization, Italy

Johannes Keizer

Email:

Tel:

Fax:

## PHARMA - Pharma Innova, Spain

See ISOCO